## Read me
RADS Adoption Checklists
The following adoption checklists are provided as general guidance for stakeholders to assist in the adoption and implementation of RADS. The checklists are not intended to cover all aspects of the RADS adoption process. Rather, they highlight activities that stakeholders should perform within the different stages of the adoption process. Checklist 1 - Familiarisation with RADS: A list of RADS educational Information for stakeholders to consider before planning to adopt RADS. Checklist 2 - Planning to adopt RADS: Activities for stakeholders to undertake when planning to adopt RADS, including project management, project planning and impact analysis. Checklist 3 - Preparing to adopt RADS: Activities for stakeholders to undertake when preparing to adopt RADS, including the current asset management environment, data mapping and data migration. Checklist 4 - Rolling-out of RADS adoption: Acitivities for stakeholders to undertake to ensure that they are prepared to go live.
Disclaimer All information provided by Austroads is for general information purposes only and should not be relied upon as the basis for making business, legal or any other decisions. While Austroads and its consultants endeavour to ensure that any and all information provided is accurate, neither Austroads nor its consultants make any representations or warranties of any kind as to the completeness, accuracy or suitability of any information provided. Austroads encourages stakeholders to undertake an internal evaluation of the information provided and consult with their asset management providers to confirm the accuracy of any mapping.

## Checklist 1 - Familiarisation
Checklist 1 - Familiarisation with RADS
No. | Checklist items | R | Notes
1 | Understanding RADS
Review the latest version of RADS
Review the Austroads report "Adoption of the Road Asset Data Standard"
 Section 1 - Introduction
 Section 2 - Road Asset Data Standard
 Section 3 - How to Adopt the Road Asset Data Standard
 Section 4 - RADS Adoption Case Studies
View available webinars at austroads.info/past-webinars

## Checklist 2 - Planning
Checklist 2 - Planning to adopt RADS
No. | Checklist items | R | Notes
1 | Project management
Assign a person/team to oversee/manage the adoption of RADS
Determine if additional people are required to undertake pre-implementation activities
Determine if there are third parties that can assist you with your transition (e.g. AMS providers etc)
2 | Project planning
Set deliverables and expectations
Assess strengths, weaknesses, opportunities, threats
Develop a project management plan
3 | Impact analysis
Assess internal departmental/organisational impacts of RADS adoption
Assess impacts on internal/external systems/processes
Assess external stakeholder impacts of RADS adoption
Prepare impact assessment management processes
4 | Resources and funding
Confirm funding available for RADS adoption
Determine internal skills/expertise needed for the project
5 | Consultation plan
Discuss RADS adoption process with internal areas
Discuss RADS adoption with asset management service provider
Discuss RADS adoption with other third parties involved in data collection/management
6 | Communication planning
Determine who will need to be informed of RADS adoption
Determine when they will need to be informed
Determine the best means to inform stakeholders of RADS adoption
7 | Training planning
Determine who will require training
Determine how training will be delivered

## Checklist 3 - Preparing
Checklist 3 - Preparing to adopt RADS
No. | Checklist items | R | Notes
1 | Project management
Confirm resource requirements for adopting RADS
Confirm the timeframe and cost for implementation
Identify any risks that need to be managed
2 | Understanding your current asset management environment
Review Section 3 of the report - How to Adopt the Road Asset Data Standard
Assess current asset management environment. Refer to Appendix A of the report - RADS Analysis of Current Asset Management Environment
Identify any systems that use or rely upon the relevant asset data. Develop a systems integration process to manage the transition of these systems to RADS
Consider business goals and the data required to make informed decisions
3 | Data cleansing
Cleanse your data and data sets to remove duplicate, irrelevant, incorrect data etc. Refer to Appendix A of the report - RADS Analysis of Current Asset Management Environment
4 | Data mapping
For information on undertaking the data mapping exercise, review Section 3 of the report - How to Adopt the Road Asset Data Standard
Map your data to RADS using RADS Data Dictionary & Mapping Template
Provide data mapping to asset management service provider
5 | Data migration
For information on how to migrate data, review Section 3 of the report - How to Adopt the Road Asset Data Standard
Review the machine readable files
Provide the machine readable files to your asset management service provider
Discuss and confirm the data migration approach with your asset management service provider
Confirm the process for user acceptance testing (UAT)
Complete data migration

## Checklist 4 - Rolling out
Checklist 4 - Rolling-out of RADS adoption
No. | Checklist items | R | Notes
1 | Confirming that datasets align with RADS
Undertake quality check to confirm data now aligns with RADS
Review and triage data no covered by RADS
2 | Systems update
Implement the process to update any systems that use or rely upon the RADS compliant asset data
Undertake testing to ensure systems are compliant with RADS
3 | Confirm organisation readiness
Update processes, documents, reports, websites, etc. to reflect RADS
4 | Communication
Develop/release communication materials notifying adoption of RADS
Communicate changes to data collectors, users of the data etc
Ensure contractors and third parties that collect or use the asset data have updated their processes and systems to reflect RADS
Update contracts with data collectors to require RADS compliant data to be provided
5 | Training
Undertake training with all relevant stakeholders
6 | Review project
Review project deliverables and expectations to determine if they have been met
Review lessons learnt
7 | Future RADS releases
Develop a process to capture and adopt future releases of RADS
8 | Collection of additional and/or better quality data
Assess the coverage and completeness of RADS compliant road asset data collected
Determine whether additional and/or better quality data shoud be collected